## Rate 63 commitment general
R63 commitment form | Supplier Name |  | UKAD |  |  |  |  | Date | 2015-03-27
| Supplier Responsible Name | Supplier Responsible Name | Benoit Delvincourt
Scope of reply - whole group, or only specific plants within group |  |  |  | NA
Company is able to ramp-up to rate 63 through to July 2018 (Station 40) | [5 empty] | Yes | Yes | No
- If no, where in the ramp-up is the blockage point reached ? | [5 empty] | Date / Rate
Please refer to the attachement, station 40 rate curve
- If yes, do you have precise actions required to achieve R63 ramp-up? | [5 empty] | Yes | Yes | No
Please provide top level roadmap of actions / milestones required to achieve R63 |  |  |  |  | Action / Milestones |  |  | Dates
Summary of specific actions needed to achieve R63 (leave blank if no actions required) |  |  |  |  | New Heating Furnace, allready ordered, commissionning in progress |  |  | 2015-04-01
[5 empty] | Building Extension for heating furnaces |  |  | end 2016
[5 empty] | New furnaces if necessary |  |  | end 2017
Please add rows if necessay
Summary of key points (Please provide additionnal details or action plans as attachements)
Existing capacity limitations (buildings, machines...), if any, and their associated mitigation plan vs the required Airbus A320 family ramp-up, |  | Heating Capacity, extension of forge building decided in order to put new furnaces. 2 new furnaces could be invested if required by the total Load.
Capital investment & resource management plan with the ultimate date to launch investment vs the required Airbus A320 family ramp-up (NOTE : no Airbus funding) (Main figures and allocations) |  | Investment engaged to increase capacity 1,5 to 5M€ depending on the projected load.
Preliminary list of the sub-tiers you consider as ‘critical’ and the actions you plan to engage to bring them up to speed
Any other enabler that is necessary to meet this unprecedented ramp-up, including but not limited to, any specific action required on Airbus side.

## z (hidden)
Yes | investment
No | refurbishment
surge